## Work Breakdown Structure
RomantiQ
|  |  |  | Defining Phase |  |  |  | Design Phase | [9 empty] | Implementation |  |  | Testing and Debugging |  | Producing Documentation |  |  | Creating Demo
|  | Define Resources |  |  | Define Schedule | User Experience Design | User Interface Design |  |  | Database Design |  |  |  | UML Diagram |  |  | Implementing Database | Implementing Client Side | Implementing Server Side | Test Database | Test Client Side | Test Server Side | Technical Documentation | Choose Role | Choose Location | Choose Schedule | Make Raw Video | Edit Video
| Define Tools |  | Define Human Resources |  |  | Screen Flow Diagram | Design Prototype |  | ERD |  | Normalization | Class Diagram | Usecase Diagram |  | Sequence Diagram | Activity Diagram |  |  |  | Debug Database | Debug Client Side | Debug Server Side | Proofreading |  |  |  |  | Choose BGM
Define Software | Define Hardware |  |  |  |  | Design Prototype | Modify Unsatisfied Parts |  |  |  | Data Dictionary | Data Description | Usecase Description | [6 empty] | Document test results | Document test results | Document test results
[6 empty] | Modify Unsatisfied Parts | [13 empty] | Proofreading | Proofreading | Proofreading

## Predecessor Table
No | Task | Duration (Day(s)) | Predessor
A | Define Resources | 3 | Start
B | Define Schedule | 2 | Start
C | User Experience Design | 7 | A+B
D | User Interface Design | 15 | C
E | Database Design | 13 | A+B
F | UML Diagram | 20 | A+B
G | Implementing Database | 18 | E
H | Implementing Client Side | 20 | D+F
I | Implementing Server Side | 27 | D+F
J | Test Database | 18 | G
K | Test Client Side | 15 | H
L | Test Server Side | 24 | I
M | Technical Documentation | 15 | J+K+L
N | Choose Role | 2 | M
O | Choose Location | 3 | M
P | Choose Schedule | 2 | M
Q | Make Raw Video | 20 | N+O+P
R | Edit Video | 14 | Q
Critical Path = Start,A,C,D,I,L,M,O,Q,R,End

## Resource Table
No | Task | Duration (Day(s)) | Predessor | Resources
A | Define Resources | 3 | Start | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
B | Define Schedule | 2 | Start | Nanda Aung
C | User Experience Design | 7 | A+B | Arkar Min Khant | *
D | User Interface Design | 15 | C | Arkar Min Khant | *
E | Database Design | 13 | A+B | Nanda Aung, Thet Maung Maung Toe
F | UML Diagram | 20 | A+B | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel
G | Implementing Database | 18 | E | Nanda Aung, Thet Maung Maung Toe
H | Implementing Client Side | 20 | D+F | Sie Thu Ko, Thet Paing Oo, Arkar Min Khant
I | Implementing Server Side | 27 | D+F | Thet Maung Maung Toe, Mya Thet Chel | *
J | Test Database | 18 | G | Nanda Aung, Thet Maung Maung Toe
K | Test Client Side | 15 | H | Sie Thu Ko, Thet Paing Oo, Arkar Min Khant, Thet Maung Maung Toe
L | Test Server Side | 24 | I | Thet Maung Maung Toe, Mya Thet Chel | *
M | Technical Documentation | 15 | J+K+L | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
N | Choose Role | 2 | M | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel
O | Choose Location | 3 | M | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
P | Choose Schedule | 2 | M | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel
Q | Make Raw Video | 20 | N+O+P | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | *
R | Edit Video | 14 | Q | Nanda Aung, Thet Maung Maung Toe, Sie Thu Ko, Arkar Min Khant, Thet Pain Oo, Mya Thet Chel | * | Critical Path = Start,A,C,D,I,L,M,O,Q,R,End

## Resource Leveling
Before Leveling
A | 6 | 6 | 6
C |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
D | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
I | [25 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
L | [52 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
M | [76 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
O | [91 empty] | 6 | 6 | 6
Q | [94 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
R | [114 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
B | 1 | 1
E |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
F |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G | [16 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
H | [25 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
J | [34 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
K | [45 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
N | [91 empty] | 6 | 6
P | [91 empty] | 6 | 6
| 7 | 7 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 18 | 18 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1
After Leveling
A | 6 | 6 | 6
C |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
D | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
I | [25 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
L | [52 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
M | [76 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
O | [91 empty] | 6 | 6 | 6
Q | [94 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
R | [114 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
B | 1 | 1
E |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
F |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G | [23 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
H | [25 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
J | [58 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
K | [45 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
N | [91 empty] | 6 | 6
P | [92 empty] | 6 | 6
| 7 | 7 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 18 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1